## For Gantt Chart Presentation.
Serial No. | Maintenance Phase | Trade(working on that) | 500 Hrs scheduled Inspection | 1000 Hrs scheduled Inspection | 1500 Hrs scheduled Inspection
1. Acceptance Phase
1 | Documents Check | All Trade | 1st day | 1st day | 1st day
2 | General Inspection | All Trade | 2nd day | 2nd day | 2nd day
3 | Power-On Checks | Aiframe ,AVNCS,Electro Mech Trade
4 | Hydrualic Ops Checks | Air Frame ,Elecrto Mech Trade
5 | Ground Run | Airframe,Engine,Electromech,AVNCS
6 | Engine Preservation | Aiframe,Engine,Electro Mech Trade
7 | Aircraft Defueling | Aiframe,Engine,Electro Mech Trade
2. Removal Phase
8 | seats removal | Airframe,Electro Mech ,Weapon Trade | 3rd day | 3rd day | 3rd day
9 | Access panels removal | All Trade | 4th day | 4th,5th day | 4th,5th day
10 | Engine removal | Airframe,Electro Mech,Engine Trade
11 | Hydrualic sys components removal | Air Frame,Electro MechTrade | 5th day | 6th day,7th day | 6th,7th day
12 | Pneumatic system removal | Airframe Trade | 6th,7th,8th,9th day | 8th,9th,10th,11th day | 8th,9th,10th,11th day
13 | Fuel system removal | Airframe,Electro Mech Trade
3. Inspection Phase
14 | Structural inspection | All Trade | 10th,11th,12th day | 12th,13th,14th,15th day | 12th,13th,14th,15th,16th day
15 | Corrosion inspection | All Trade
16 | Fuel tanks inspection | All Trade
17 | Cleaning and Lubrication | All Trade
4. Intsallation Phase
18 | Hydrualic sys components install | Airframe,Elecetro Mech Trade | 13th,14th day | 16th,17th,18th day | 17th,18th,19th day
19 | Pneumatic system install | Airframe Trade | 15th,16th day | 19th,20th day | 20th day
20 | Fuel system install | Airframe,Elecetro Mech Trade |  |  | 21th day
21 | Engine install | Airframe,Electro Mech,Engine Trade | 17th day | 21th day | 22th day
22 | Cockpit Pressurization Check | Airframe,Electro Mech Trade | 18th day | 22th day | 23th day
23 | Hydrualic system ops Checks | Airframe,Electro Mech Trade
24 | Flt Controls rigging | Airframe,Electro Mech Trade | 19th,20th day | 23th,24th day | 24th,25th day
25 | Independent Checks by QC & QA | Airframe,Elecrtro Mech,Engine Trade
26 | Access panels install | All Trade | 21th day | 25th day | 26th day
27 | Seats install | Airframe,Electro Mech,Weapon Trade
5.Ops Phase
28 | Aircraft symmetry Check | Airframe,Electro Mech,Engine Trade | 22th day | 26th day | 27th,28th day
29 | Fuel leak test | Airframe,Electro Mech,Engine Trade |  | 27th day
30 | Drop tank circuit & Jettison Check | Airframe,Electro Mech,Engine Trade
31 | Power-On Checks | Airframe,Electro Mech,AVNCS Trade
6. Production Phase
32 | Full Power Ground Run | All Trade | 23th day | 28th day | 29th day
33 | Fuel transfer Check | Airframe,Electro Mech,Engine Trade
34 | Readiness for QSD | All Trade | 24th day | 29th day | 30th day
35 | QSD | All Trade | 25th day | 30th day | 31th day
36 | Taxi test | All Trade | 26th day | 31th day | 32th day
37 | FCF | All Trade
|  | Total Days: | 26 | 31 | 32
0.Note:
Any person can edit/add/remove these days,phases,trade etc allotment Just clicking bottom given, Edit Sheet Button and can download in excel etc (but special admin password sould be there for security else then of login password).
0.Note:
All trades should be saved in both segment Maintenance and Staggering .The duty roster of all trades should be there in both segments like choosing Sqn and then S.no ,Trade,Designation,Rank ,Pak no, Name ,Disposal{present and leave or absent option(remarks also)} ,reporting time,leaving time. TMA due date,NRM Date,GDE Date ,calculation and keeping Anual record of Abenties/leaves.
standard Calender +Time attach to software, additional if weather forcast of different cities of pakistan
1. Note:
From staggering Flying Hours segment, each aircraft as come nearby to mentioned hours ,has been decided to come Maintenance of these respective Hrs scheduled Inspection .It can only be delayed to +5 or +10 Hrs if Air headquarter grants permission according to need of flying and no major problem of aircraft.
2. Note:
If any aircraft comes to maintenance segemnt due to some major issues, it is known as unscheduled maintenance of only that part.
But additionally , if reported aircraft is -15 or 20 hrs nearby to any (scheduled inspection defined flying hours) of that respective aircraft,
then it will go for complete scheduled insepction steps of that nearby hours inspection.
3. Note:
These Days are working days(for projected ideal date for readiness from induction date 1st day) , and there might be leave of concerend staff,holidays,MICAP(Mission Impaired Capability Awaiting Parts) delays days..
It might be case that you did some task earlier so we can manually enter which task we have done and remarks etc , at the end of every day report status .So, there will be three graphs ,one is gantt chart , 2nd simple graph from these ideal defined days and other in comparison will define our current working days accomplishement speed.
Percentage and different graphs can be shown , to show task compleition rate (how much out of 100 has been done).